Reg. No. ________

Karunya University

(Declared as Deemed to be University under Sec.3 of the UGC Act, 1956)

End Semester Examination – November / December 2008

Subject Title: 	SOFTWARE PROJECT MANAGEMENT			              Time : 3 hours

Subject Code: 	CA350			         						               Maximum Marks: 100

#### Answer ALL questions (5 x 20 = 100 Marks)

1.	Compulsory:

What are the activities that you suggest to select the most appropriate methodologies and techniques for the project?

2.	a. 	Explain in detail the stepwise project planning activities.							(15)

b. 	Identify the stakeholders in the Karunya University Payroll projects. 				(5)

(OR)

3.	a. 	What are the different forms of programmes? Explain in detail. 					(10)

b. 	Briefly explain benefits management. 											(10)

4.	a. 	Briefly explain activity-on-arrow network with suitable example. 					(15)

b. 	List the objectives of activity planning. 											(5)

(OR)

5.	a. 	Match the following causes a) to d) to their possible effects i to iv. The relationships are not

necessarily one to one. Explain the reasons for each match.

Causes:

a)	staff inexperience			b) lack of top management commitment

c) 	new technology			d) users uncertain of their requirements

Effects:

i. testing takes longer than planned		ii. planned effort and time for activities exceeded

iii. project scope increases				iv. time delays in getting changes to plans agreed.   (8)

b.	What are the advantages of PERT technique? Explain PERT Technique. 			(12)

6.	a. 	Sketch the project control cycle and briefly explain creating the framework. 			(15)

b. 	A software developer working on Karunya University payroll system has written the first 250 lines of a Java program that is estimated to require 500 lines of code.  Explain why it would be unreasonable to assume that the programming task is 50 % complete. How might you make a reasonable estimate of how near completion it might be? 				(5)

(OR)

7.	a. 	What are the different types of contract? Explain with advantages and disadvantages. (15)

b. 	It is easy to see why passing on fluctuation in equipment costs may be advantageous to the contractor. However, is there any advantage to the customer in such an arrangement? (5)

8.	Briefly explain:		a.	Decision making 			b.	Leadership

(OR)

9.	a. 	Briefly explain documenting the project plan. 									(15)

b. 	A software development department wants to improve productivity by encouraging the reuse of existing software components. It has been suggested that this could be encouraged through financial rewards. To what extend do you think this could be done? 			(5)