Reg. No. ________

Karunya University

(Declared as Deemed to be University under Sec.3 of the UGC Act, 1956)

End Semester Examination – November / December 2008

Subject Title: 	PROJECT APPRAISAL MANAGEMENT			              Time : 3 hours

Subject Code: 	MS328			         						               Maximum Marks: 100

#### Answer ALL questions (5 x 20 = 100 Marks)

1.	Case Study: [Compulsory]

Ramesh has been appointed project manager of the Sansui and Co., a new sensor manufacturing process project. Sensors are extremely price – sensitive, and Sansui has done a great deal of quantitative work so it can accurately forecast changes in sales volume relative to changes in pricing.

The company President, Jack has considerable faith in the firms sensitivity model and insists that all projects that affect the manufacturing costing of sensors be run against the sensitivity model in order to generate data to calculate the return on investment. The net result is that project managers, like Ramesh, are under a great deal of pressure to submit realistic budgets so go or no – go projects decisions can be made quickly. Jack has canceled several projects that appeared marginal during their feasibility stages and recently fired a project manager for over estimating project costs on a new model sensor. The project was killed very early in the design stage and six months later a competitor introduced a similar sensor that proved to be highly successful.

Ramesh’s dilemma is how to go about constructing a budget that accurately reflects the cost of the proposed new manufacturing process. He is an experienced executive and feels comfortable with his ability to come close to estimating the cost of the project. However, the recent firing of his colleague has made him a bit gun – shy. Only one stage out of the traditional four. Stage sensor manufacturing process is being changed so he has detailed cost information about a good percentage of the process. Unfortunately, the tasks involved in the process stage being modified are unclear at this point. Ramesh also believes that the new modification will cause some minor changes  in the other three stages, but these changes have not been clearly identified. The stage being addressed by the project represents almost 50 percent of the manufacturing cost.

Question:

Under these circumstances, would Ramesh be wise to pursue a top-down or a bottom-up budgeting approach? Why? What factors are most relevant here?

2.	Explain the role of a Product Manager.

(OR)

3.	How to choose software for project elevation.

4.	Explain the rules and objectives for network.

(OR)

5.	What is Master network explain.

6.	Differentiate between UNIDO and Little Mirrlks Approach?

(OR)

7.	Explain the role of PAD and PIB (Project Appraisal Division) and (Public Investment Board).

8.	Discuss the difference between total float, free float and independent float.

(OR)

9.	What are the causes of cost over run? How to precaution it?