Reg. No. ________

Karunya University

(Declared as Deemed to be University under Sec.3 of the UGC Act, 1956)

Trimester Examination – September / October 2009

Subject Title: 	CONSTRUCTION PLANNING, SCHEDULING AND CONTROL

Time : 3 hours

Subject Code: 	CE376			         						           Maximum Marks: 100

Answer ALL questions (5 x 20 = 100 Marks)

1. 	Compulsory:

The following table gives the activities of a construction project and other relevant information.

a.	What is the normal project length and the minimum project length?

b.	Determine the minimum crashing costs of schedule ranging from normal length down to and including the minimum length schedule.

c.	What is the optimal length schedule duration of each job for your solution?

Overhead of the project is Rs. 60 per day.

| Activity i-j | Normal Duration (Days) | Crash Duration (Days) | Cost of Crashing (Rs. Per day) |
| --- | --- | --- | --- |
| 1 – 2 1 – 3 1 – 4 2 – 4 3 – 4 4 – 5 | 9 8 15 5 10 2 | 6 5 10 3 6 1 | 20 25 30 10 15 40 |

2.	How will you define precedence relationship among activities?

(OR)

3.	Write elaborate description of Coding Systems used in Construction planning.   Explain any coding system for Example MASTERFORMAT.

4.	a.	Explain Financial Accounting systems and Cost accounts.							(10)

b.	Enumerate schedule control.													(10)

(OR)

5.	Write notes on

a	The Cost control problem 		b.	Project Budget.						(2 x 10 = 20)

6.	Sort out Statistical Quality Control with sampling by variables	.

(OR)

7.	What do you understand by Quality Control?   Explain with example.

8.	Enumerate Centralized Database management Systems.

(OR)

9.	Write notes on Information transfer and flow.