Reg. No. ________

Karunya University

(Karunya Institute of Technology and Sciences)

(Declared as Deemed to be University under Sec.3 of the UGC Act, 1956)

End Semester Examination – April/May – 2016

Subject Title :	CONSTRUCTION MANAGEMENT					      	     Time : 3 hours

Subject Code:	12CE242										       Maximum Marks: 100

#### Answer ALL questions

PART – A  (10 x 1 = 10 MARKS)

1.	List out the objectives of CONSTRUCTION MANAGEMENT.

2.	Collusive tendering is an ethical impropriety. Discuss.

3.	Name any 2 factors that have to be considered in preliminary planning.

4.	What are stages of construction?

5.	What are the uses of network?

6.	The path in any network in which there is NO FLOAT is called ___________.

7.	Name the different types of contract.

8.	Name any two acts that are applicable for Construction Industry.

9.	What is cash book and what it contains?

10.	High inventories do not affect cash flow – Say true or false.

PART – B  (5 x 3 = 15 MARKS)

11.	How is Public Works Department organized?

12.	What is a project report? What information should a project report furnish?

13.	State any 3 do’s and don’ts in networking with sketches.

14.	Give any three types of contract and state its applicability.

15.	Surplus and shortage in Stores will affect the progress of any project. Can you justify?

PART – C  (5 x 15 = 75 MARKS)

16.	a.	List the various stakeholders in a Construction Project.							    (3)

b.	Give the organization structure of Public Works Department listing out the functions of any 4 Officers.																(3x4)

(OR)

17.	a.	State and define various classes of establishment.									    (3)

b.	What are the various stages of Construction Planning? Discuss about each in detail.	  (12)

18.	a.	Explain with reference to investigation and collection of data –

i.	Reconnaissance Survey.													    (4)

ii.	Preliminary Survey.														    (6)

b.	What is the difference between Administrative Approval and Technical Sanction?	    (5)

(OR)

19.	a.	Materials constitute to nearly 65% of the project value. Perfect planning for materials will 	result in higher profit. Can you justify your answer with 2 examples?				(2x3)

b.	You are the Project Manager of a Construction Project. You have workers from all parts of the country. State some proactive steps and measures that you would initiate to motivate workers of your project site.												 	    (5)

c.	Spending on training manpower and staff will give returns for a Company. State how and 	on what the training should be given.											    (4)

[P.T.O]

20.	a.	Construct a network diagram for a project comprising the following activities A, B, C, D, 	E, F and G and having the following relationships. Number the events and also indicate the 	activity duration in the network.												    (6)

i.	A is the initial activity of the network;

ii.	A precedes activities B, C and D;

iii.	B precedes E;

iv.	C precedes F;

v.	D precedes G;

vi.	E precedes F;

vii.	F precedes G;

viii.	G is the terminal activity of the project.

Duration of activities for A, B, C, D, E, F and G are 3, 6, 16, 10, 8, 5 and 3 days respectively.

b.	Identify the critical path.														    (3)

c.	Find EST, EFT, LST and LFT for all activities.									           (3)

d.	Find also total float, free float and independent float.								           (3)

(OR)

21.	A small project is composed of 7 activities whose time estimates are listed in table below. Activities are identified by their beginning i and j numbers:

| ACTIVITY | ESTIMATED DURATION (weeks) |  |  |
| --- | --- | --- | --- |
|  | OPTIMISTIC (to) | MOST LIKELY (tL) | PESSIMISTIC (tP) |
| 1-2 | 1 | 1 | 7 |
| 1-3 | 1 | 4 | 7 |
| 1-4 | 2 | 2 | 8 |
| 2-5 | 1 | 1 | 1 |
| 3-5 | 2 | 5 | 14 |
| 4-6 | 2 | 5 | 8 |
| 5-6 | 3 | 6 | 15 |

a.	Draw the project network and identify all paths through it.							        (5)

b.	Find the expected duration (tE) for each activity.									        (2)

c.	Calculate the early and late occurrence times for each node. Assume the project scheduled time as equal to the early occurrence time of the end event of the project.			   		        (3)

d.	Calculate the slack for each event and identify the critical path. What is the expected project duration (Te).															                (3)

e.	Calculate the variance and standard deviation of the project length.					         (2)

22.	Write notes on the following (any 3):												      (3x5)

a.	Payment of Wages Act, 1936.

b.	The Act which stipulates the payment of minimum wages to workers in Construction Project Sites.

c.	There would be dispute between Owner and Contractor in some area or other. How the disputes are solved? Discuss on the Act which governs disputes.

d.	Legal Implications of Contract.

(OR)

23.	a.	What are the advantages of Tendering?											        (2)

b.	Give a sample TENDER NOTICE.											        (4)

c.	What are the deposits that have to be remitted by Tenderers and why?				        (3)

d.	Process of selection and acceptance of tender – What would be the procedure adopted if the tender received are much higher than the estimated cost of the project.			    			        (6)

24.	Explain about the following:

a.	M  book – recording, checking and maintaining.									        (4)

b.	Bills and types.															        (4)

c.	How are Stores classified? Discuss the maintenance procedures in detail.			                (7)

(OR)

25.	Write notes on the following:

a.	Budget Estimate and Revised Estimate.	(4)   		b.	Ledger Accounts.   		        (2)

c.	Imprest Account; 					       (2)		d.	Cash book in PWD. 		        (3)

e.	Accounting surplus and shortage in Stores.										        (4)