# Reg. No. ________

Karunya University

(Karunya Institute of Technology and Sciences)

(Declared as Deemed to be University under Sec.3 of the UGC Act, 1956)

End Semester Examination – April/May – 2016

# Subject Title:	PROJECT MANAGEMENT 						        Time: 3 hours

# Subject Code:	15MS3038								              	 Maximum Marks: 100

Answer ALL questions (5 x 20 = 100 Marks)

1.	Compulsory (Case Study):

According to the Project Management Institute (PMI, 1996), project risk management includes the processes concerned with identifying, analyzing and responding to project risk. It includes maximizing the results of positive events and minimizing the consequences of adverse events. In the automotive industry, lead time to develop and industrialize new vehicles is significantly decreasing in order to achieve competitiveness with the new models. This fact makes difficult to detect possible errors related to the associated components and process and it also reduces reaction time. To define a process to detect possible risks and to take retaining actions on time are essential to achieve success in the new models launch. On the other hand, big vehicle manufacturers expect of their suppliers to design the different components according to technical specifications. In this way, design departments at the manufacturer manage the vehicle components design together with selected suppliers.

It is the case of the Spanish business unit of an American multinational company which supplies automotive components. The company employs approximately 60,000 people in 185 facilities located in 26 countries. It is worth to mention that the company supplies to the most important vehicle constructors, developing and producing active and passive safety systems. The global sales during the year 2010, last year from which data are available, were around 12 billion Euros, distributed among the following business lines: 1. Passive safety (OSS, Occupant Safety Systems): steering wheel, airbag modules, seatbelts and bags development. 2. Active safety: video and radar sensors to enable advanced drier assist functionality, automatic emergency braking and collision mitigation braking. 3. Active/passive safety integration: collision avoidance and mitigation systems (radio frequency systems, etc.). 4. Components: engine valves, entry systems and presence control systems. OSSE is the European unit for the development and production of passive safety products. This unit headquarters are located in Alfdorf (Germany) and it has 27 production plants located in 16 countries of the European Community. The business unit in which this case is being developed belongs to the European unit and it is called OSSE Spain-Portugal (OSSE-EP). OSSE-EP employs 2,000 workers distributed among 5 production plants and 3 R&D centers. The main offices are placed in Vigo and it can be found the Economical Controlling and Project Management departments. The Project Management department is responsible for the coordination of all the activities related with the project development before the serial production.

Analysis and diagnose of project risk management procedure

The figure shows the flow described in the current project risk management procedure.

Figure: Project risk management flow. OSSE-EP´s procedure 				        [P.T.O]

The current procedure suggests, also, that the risk project should be included in the Reporting Corporate System (RCS). This system is accessible though the 599 company´s intranet and it works as a Project Management, Purchasing and Operations reporting database. RCS shows two different possibilities: on the one hand, it offers the option to enter risks and, on the other hand, it also gives the option to register issues. Nowadays, most of the time, this tool is being considered for the issues entry and not for the risks one, it means, instead of using RCS as a prevention system it is used to report to the managers those risks that have already become problems for which is needed to find a solution. Apart from the PRM procedure and RSC, the company has another element available to show the project risk up, this is the SRM (Status review Meeting). These meetings take place once a month and the main objective is to report the different areas responsible about the project with most critical points. And, it is worth to mention that different documents area created during the project´s development for the information exchange with the customer. In this sense, some customers request a checklist for the risks identification. In summary, currently OSSE-EP has different elements available for the project risk management. Nevertheless, all these elements are being used only from time to time, it means, the current risk management is not followed in a methodological way along the project´s lifecycle. Using PMI standard analysis, the following points have been detected in the current project risk management system:

a.	The risk management is not planned in such a way that the different phases of the process are included in the project planning.

b.	The list of risk categories presented in the procedure is very wide and some of the defined risks show ambiguity.

c.	The procedure defines four phases for the risk management (identification, analysis, action plan and monitoring). The PMI® makes a more detailed division and identifies six phases (plan, identification, qualitative analysis, quantitative analysis, action plan and monitoring/control).

d.	The procedure establishes a numeric scale for the impact and probability. For the risks with a total rating of 12, 16 or 24, an action plan is formulated. The risks with an overall rating below 12 become part of the watch list in the risk register. The PMI®, on the other and, makes a qualitative division in terms of high, medium or low risks. This standard also includes a quantitative analysis to calculate the risk level according with economic values.

e.	The procedure doesn´t define the risk response plans in detail and it never mentions the opportunity response plans.

Taking into account the current risk management procedure, Redesign the current project risk management procedure to exploit the project resources and time in an effective and efficient way

2.	a.	Explain in detail the similarities and differences among portfolio management, program 	management, project management and Organizational Project management.		      (12)

b.	Write a short note on Project Management Office, its types and function.			 (5)

c.	Bring out the differences between the role of project managers and a Project 	Management Office.															 (3)

(OR)

3.	a.	What is Project Life Cycle? 						                                   			 (3)

b.	Explain the characteristics of Project Life Cycle with the generic life cycle structure.   (5)

c.	What are the different phases of a project? Explain with the types of phase-to-phase 	relationship, Predictive Life Cycles, Iterative, Incremental Life Cycles, & Adaptive Life 	Cycles with suitable diagrams.												      (12)

4.	Explain in detail the Project Management Process Groups (or Process Groups) and illustrate with the process flow diagram.

(OR)

5.	Explain in detail the process of Project Integration Management with its inputs, tools & techniques and outputs for each stage.

6.	Write short notes on the following:					                       			            (5x4)

a.	Components of a scope management plan. 	b.	Prototyping.

c.	Requirements Traceability Matrix.			d.	Scheduled Management Plan.

e.	Precedence Diagramming Method.

(OR)

7.	Write short notes on the following:						                                                (5x4)

a.	Reserve Analysis for cost management		b.	Cost Baseline

c.	Seven Basic Quality Tools					d.	Quality Management and Control Tools

e.	Tools and techniques used to control costs:

8.	How do you plan, acquire, develop and manage a project team for Human Resource Management? Explain in detail.

(OR)

9.	How do you plan, manage and control communications for Project Communications Management? Explain in detail.