Reg. No. ________

Karunya University

(Karunya Institute of Technology and Sciences)

(Declared as Deemed to be University under Sec.3 of the UGC Act, 1956)

Supplementary Examination – June 2016

Subject Title :	CONSTRUCTION MANAGEMENT					      	     Time : 3 hours

Subject Code:	12CE242										       Maximum Marks: 100

#### Answer ALL questions

PART – A  (10 x 1 = 10 MARKS)

1.	Define Construction Planning.

2.	Write down various construction of any project.

3.	What is activity?

4.	What is the use of network?

5.	What are the types of contracts?

6.	Why tendering is adopted in construction projects?

7.	Expand and explain what CPM is?

8.	What is meant by Estimate?

9.	How psychology of workers affect productivity?

10.	What is cash book?

PART – B  (5 x 3 = 15 MARKS)

11.	Write short notes on organisation and various types.

12.	How is PWD organized?

13.	Mention few do’s and dont’s in networking.

14.	Write down the laws of construction.

15.	State any one discrepancy that can be observed during stock verification and explain.

PART – C  (5 x 15 = 75 MARKS)

16.	Explain briefly the functions of Construction Management.

(OR)

17.	Explain about the various types of organization with examples.

18.	Explain the various types of contracts and their applicability.

(OR)

19.	a.	Define scheduling. What are the factors affecting scheduling?						    (7)

b.	Explain briefly about: (i) Minimum Wages Act, 1948; (ii) Payment of Wages Act, 1936.

(8)

20.	Draw the network. Determine the critical path and its duration.  Also determine all the floats.

Activity                            Duration (days)

1-2                                       8

1-3                                      10

1-4                                       5

2-7                                       6

3-4                                       3

4-5                                       7

4-7                                       0

5-6                                       4

5-7                                       3

5-8                                       6

6-8                                       5

7-8                                       5

[P.T.O]

(OR)

21.	a.	What are the 3 time estimates of activities duration in PERT technique?				  (10)

b.	Write differences between CPM and PERT.										    (5)

22.	What are the advantages calling for tenders? Explain in detail about a tender document.

(OR)

23.	a.	Write short notes on: (i) Payment of Wages Act 1936; and (ii) Legal implication of 	contract.																		    (8)

b.	How disputes are solved if any arises between Contractor and Client? Write notes on the Act which governs this issue.													    (7)

24.	What do you mean by stores and how are they classified?

(OR)

25.	Explain briefly the following:

a.	Record measurement book.

b.	Types of bills.