Reg.No. ____________

UNIVERSITY

(Karunya Institute of Technology & Sciences)

(Declared as Deemed-to-be University under Sec.3 of the UGC Act, 1956)

End Semester Examination – Nov/Dec – 2016

|  |  | Semester : | 2016-17 ODD |
| --- | --- | --- | --- |
| Code : | 14CE2028 | Duration : | 3hrs |
| Sub. Name : | Construction Management | Max. marks : | 100 |

ANSWER ALL QUESTIONS (5 x 20 = 100 Marks)

| Q. No. | Sub Div. | Questions | Course Outcome | Marks |
| --- | --- | --- | --- | --- |
| 1. | a. | What are the objectives, importance and scope of construction Management? | CO1 | 10 |
|  | b. | What is abstract report and detailed project report? Explain in detail the main points in detailed report | CO1 | 15 |
| (OR) |  |  |  |  |
| 2. | a. | Find out the economical material Material A; Material B. Strength; 20000 units; 30000 units. Cost; Rs. 4000/tonne; Rs.4250/tonne. | CO1 | 5 |
|  | b. | Briefly explain the four analysis involved in feasibility of a project | CO1 | 15 |
| 3. | a. | Define break even analysis. What are the advantages and disadvantages in breakeven analysis? | CO1 | 5 |
|  | b. | A well planned work is half done. Explain the advantages and stages of planning | CO1 | 15 |
| (OR) |  |  |  |  |
| 4. | a. | The maintenance project of a building consists of 10 activities. The predecessor relationship are identified by their numbers as indicated below. Draw the network diagram for the project. Activity; Identification; Activity; Identification. P; (1,2); U; (4,5). Q; (2,3); V; (4,7). R; (2,4); W; (5,8). S; (3,6); X; (6,8). T; (3,5); Y; (7,8). | CO2 | 10 |
|  | b. | ‘Specifications define the structure and furnish full project physically and technically’ write briefly its importance and types. | CO2 | 10 |
| 5. | a. | The following table lists the activities, durations and their sequence of operation for a construction project. Prepare the network and compute in a table their early start, early finish, late start and late finish times. Determine the critical path and find the total float and free float for all the activities. Activity; Duration (days); Activity; Duration (days). 1-2; 8; 4-7; 0. 1-3; 10; 5-6; 4. 1-4; 5; 5-7; 3. 2-7; 6; 5-8; 6. 3-4; 3; 6-8; 5. 4-5; 7; 7-8; 5. | CO2 | 20 |
| (OR) |  |  |  |  |
| 6. | a. | The details of a network is given below where the duration is in days. Activity; to; tm; tp. 1-2; 2; 5; 8. 1-3; 1; 4; 7. 2-3; 0; 0; 0. 2-4; 2; 4; 6. 2-6; 5; 7; 12. 3-4; 3; 5; 10. 3-5; 3; 6; 9. 4-5; 4; 6; 10. 4-6; 2; 5; 8. 5-6; 2; 4; 6. - Draw the network diagram (3) - Find the probability of completing the project within 23 days (6) - Find the critical path (5) | CO2 | 20 |
| 7. | a. | ‘Contract documents for a construction projects is to be developed based on a joint effort by the designer, owner and manager’ – discuss on items to be considered for a typical contract package. | CO 3 | 10 |
|  | b. | Gammon India Properties needs to construct a mall in Coimbatore. As a civil engineer in charge, explain the salient points a tender notice and a tender document should carry. | CO 3 | 10 |
| (OR) |  |  |  |  |
| 8. | a. | Draft a tender notice for the construction of an overhead tank for a hostel complex. | CO 3 | 5 |
|  | b | Give short account about: - Earnest Money Deposit and Security Deposit - Legal Obligation of the contract |  | 10 |
|  | b. | For establishing a cordial relationship between the owner and the contractor, type of contract selected plays a vital role. Summarize different types of contract. | CO 3 | 10 |
|  |  | Compulsory: |  |  |
| 9. | a. | Explain importance of safety | CO 3 | 4 |
|  | b. | Explain the safety benefits and the role of various parties in safety management | CO 3 | 6 |
|  | c. | Name any four software used in the field of construction management. Explain the step by step procedure in PRIMAVERA | CO 3 | 6 |
|  | d. | With the help of flowchart, explain the organizational structure of the P.W.D. | CO 3 | 4 |

ALL THE BEST

CO1: Manage the resources and labours in the construction

CO2: Plan the construction projects

CO3: Estimate the cost of the projects and evaluate the tenders