UNIVERSITY

(Karunya Institute of Technology & Sciences)

(Declared as Deemed-to-be University under Sec.3 of the UGC Act, 1956)

Reg. No. ________

End Semester Examination – April / May – 2017

Subject Title : 	PROJECT MANAGEMENT						Time : 3 hours

Subject Code: 	15MS3038				         				        Maximum Marks: 100

Answer ALL questions (5 x 20 = 100 Marks)

1.	Case Study (Compulsory):

Develop a detailed Project Scope Statement, as prescribed by Project Management Institute, for construction of a 2 BHK independent villa in Alandurai.

2.	a.	Describe the Inputs, Outputs and Tools & Techniques for the process of Plan Risk 	management and identify risks.												(10)

b.	Describe the Inputs, Outputs and Tools & Techniques for the process of Plan Schedule  	management and define activities.											(10)

(OR)

3.	a.	Explain the Earned Value method of managing project time and cost. Use a suitable 	numerical example to substantiate your answer.								(10)

b.	If PV = 4000, EV = 4500, AC = 4250. Comment on the Project performance on the basis of cost and time.														  (5)

c.	If PV = 4000, EV = 4500, AC = 4000. Comment on the Project performance on the basis of cost and time.														  (5)

4.	Describe the various Project Management processes.

(OR)

5.	a.	Describe the Inputs, Outputs and Tools & Techniques for the process of Plan Scope 	Management and collect requirements.									       (10)

b.	Describe the Inputs, Outputs and Tools & Techniques for the process of Define Scope and Create Work Breakdown structure.										(10)

6.	Using suitable Indian Examples, explain the differences between a Program, a portfolio and a project.

(OR)

7.	With suitable examples, describe the influence of Organisational structure on Projects.

8.	a.	What are the Responsibilities of a Project Manager and the competencies required for a 	project manager to fulfil his responsibilities.									(10)

b.	What is a Project Management office?  What are its responsibilities? And what are the 	various types of Project Management Office?								(10)

(OR)

9.	Using suitable Indian examples, discuss the various strategic considerations for which an organisation would initiate a project to be implemented.