Reg. No. ________

Karunya University

(Karunya Institute of Technology and Sciences)

(Declared as Deemed to be University under Sec.3 of the UGC Act, 1956)

End Semester Examination – April/May-2013

Subject Title: SOFTWARE PROJECT MANAGEMENT				      	       Time: 3 hours

Subject Code: 09IT231				       				        	      	       Maximum Marks: 100

#### Answer ALL questions

PART – A  (10 x 1 = 10 MARKS)

1.	Define the verb type approaches to build the WBS.

2.	Name any two component parts of a POS.

3.	Expand JPP.

4.	Define a Work Package.

5.	Name three separate components of a project team.

6.	What is meant by a Critical Chain?

7.	List the characteristics of an Extreme Project.

8.	Mention the conversations in COS.

9.	What is a portfolio project?

10.	Define Project Support Office.

PART – B  (5 x 3 = 15 MARKS)

11.	What are the criteria to test the completeness of a WBS?

12.	Define Slack time and mention its types.

13.	Explain Stoplight Reports.

14.	Compare the project approaches- TPM, APF and xPM.

15.	Describe the three categories of status for active projects.

PART – C  (5 x 15 = 75 MARKS)

16.	Explain the Traditional Project Management Life Cycle.

(OR)

17.	Write notes on approaches to Building Work Breakdown Structures.

18.	Explain the process of Estimating Cost.

(OR)

19.	How do you build a Project Network Diagram by Precedence Diagramming Method?

20.	Explain the steps in closing a Project.

(OR)

21.	Write notes on Establishing Team Operating Rules.

22.	Give the details of the different phases of Adaptive Project Framework with a neat diagram.

(OR)

23.	Describe two major parts of Version Scope.

24. 	Describe an example of POS for PSO Implementation project with a neat diagram.

(OR)

25.	What is Project Portfolio Management? Describe its major phases with a neat diagram.