Reg.No. ____________

End Semester Examination – Apr/May – 2018

| # Code : | # 14CE2028 | # Duration : | # 3hrs |
| --- | --- | --- | --- |
| # Sub. Name : | # CONSTRUCTION MANAGEMENT | # Max. marks : | # 100 |

ANSWER ALL QUESTIONS (5 x 20 = 100 Marks)

| Q. No. | Sub Div. | Questions | Course Outcome | Marks |
| --- | --- | --- | --- | --- |
| 1. |  | Write short notes on the various analyses carried out for understanding the viability of a project. | CO1 | 20 |
| (OR) |  |  |  |  |
| 2. | a. | Sketch the schematic diagram for feasibility study and explain. | CO1 | 5 |
|  | b. | Summarise the steps involved in planning of a project. | CO1 | 5 |
|  | c. | With the aid of flowchart, classify construction works. | CO1 | 5 |
|  | d. | Define specification. Why are specifications important? Illustrate with an example. | CO1 | 5 |
| 3. | a. | Discuss the important considerations in contracts. | CO3 | 5 |
|  | b. | Recall the different contract documents. | CO3 | 15 |
| (OR) |  |  |  |  |
| 4. | a. | Appraise the different tyes of specifications in a contract document. | CO3 | 10 |
|  | b. | Compare and contrast between earnest money deposit and security deposit. | CO3 | 6 |
|  | c. | Revise the different types of tenders. | CO3 | 4 |
| 5. | a. | With a neat sketch, explain how bar charts could be used for project scheduling. | CO2 | 8 |
|  | b. | Activity; to; tm; tp; Activity; to; tm; tp. 1-2; 2; 5; 8; 3-4; 3; 5; 10. 1-3; 1; 4; 7; 3-5; 3; 6; 9. 2-3; 0; 0; 0; 4-5; 4; 6; 10. 2-4; 2; 4; 6; 4-6; 2; 5; 8. 2-6; 5; 7; 12; 5-6; 2; 4; 6. Find the expected mean time for each of the paths. Also find the critical path as well as the expected time for the project completion. | CO2 | 8 |
|  | c. | Explain the uses and function of dummies. | CO2 | 4 |
| (OR) |  |  |  |  |
| 6. | a. | In a small construction project, there are 6 activities identified from G to L. The following relationships between the different activities: - G is the first activity to be performed - H and I can be done concurrently and must follow G - H must precede J - K must succeed I, but it cannot start until H is completed - The last operation L is dependent upon the completion of both J and K Draw and number the network | CO2 | 10 |
|  | b. | What do you understand by “work breakdown structure”? Why is it necessary? | CO2 | 10 |
| 7. | a. | Bring out the importance of safety in construction projects. | CO3 | 10 |
|  | b. | Assess the usage of expert system and artificial intelligence in construction management. | CO2 | 10 |
| (OR) |  |  |  |  |
| 8. | a. | Predict the role of designer, employer, employees and dealers in safety management. | CO3 | 10 |
|  | b. | Memorise the Fulkerson’s rules for drawing a network diagram. | CO2 | 10 |
|  |  | Compulsory: |  |  |
| 9. | a. | Assess the necessity of artificial intelligence in construction industry and brief its application. | CO2 | 10 |
|  | b. | Brief about Graphical Evaluation and Review Technique. Describe the advantages and disadvantages of GERT. | CO3 | 10 |