Reg.No. ____________

UNIVERSITY

(Karunya Institute of Technology & Sciences)

(Declared as Deemed-to-be University under Sec.3 of the UGC Act, 1956)

End Semester Examination – Nov/Dec – 2017

| Code : | 14CE2028 | Duration : | 3hrs |
| --- | --- | --- | --- |
| Sub. Name : | CONSTRUCTION MANAGEMENT | Max. marks : | 100 |

ANSWER ALL QUESTIONS (5 x 20 = 100 Marks)

| Q. No. | Sub Div. | Questions | Course Outcome | Marks |
| --- | --- | --- | --- | --- |
| 1. | a. | Classify construction works with the aid of a flowchart. | CO2 | 10 |
|  | b. | Enumerate the stages of planning. | CO2 | 10 |
| (OR) |  |  |  |  |
| 2. | a. | Explain types of contract in detail. | C03 | 15 |
|  | b. | Write specification for centering and shuttering. | CO2 | 5 |
| 3. | a. | Differentiate earnest money deposit and security deposit. | CO3 | 5 |
|  | b. | The following activities are involved in the construction of a auditorium. The predecessor relationship are identified by their numbers given in table.1. Develop and draw the step by step development of network diagram and number it according to Fulkerson’s rule. Table.1. Activity; Identification; Activity; Identification. A; 1,2; F; 4,5. B; 2,3; G; 4,7. C; 2,4; H; 5,8. D; 3,6; I; 6,8. E; 3,5; J; 7,8. | CO1 | 15 |
| (OR) |  |  |  |  |
| 4. | a. | Define the terms i. Activity ii. Event iii. dummy. | CO3 | 5 |
|  | b. | Explain the methods of scheduling with suitable examples. | CO2 | 15 |
| 5. |  | Formulate the slack of each event and critical path of the network shown in Figure 1. Using Program Evaluation and Review Technique. Consider the scheduled date of completion as 54 weeks. | CO2 | 20 |
| (OR) |  |  |  |  |
| 6. | a. | Evaluate the critical path and EST, LST and other estimates for the given network in Table 2 using Critical Path Method. Table 2. Activity; Event; Predecessor; Successor; Duration. A; 1-2; -; B, C; 2. B; 2-3; A; D, E; 7. C; 2-4; A; F, I; 2. D; 3-6; B; J; 8. E; 3-5; B; H; 10. F; 4-5; C; H; 8. H; 5-8; E, F; I; 9. I; 4-7; C; K; 14. J; 6-8; D; L; 5. K; 7-8; D; L; 6. L; 8-9; H, J, K; -; 8. | CO2 | 20 |
| 7. | a. | Explain break even analysis with an example. | CO1 | 10 |
|  | b. | Predict the role of designer, employer, employees and dealers in safety management. | CO1 | 10 |
| (OR) |  |  |  |  |
| 8. |  | Construct the organizational structure of PWD and discuss the responsibilities of the officers. | CO1 | 20 |
|  |  | Compulsory: |  |  |
| 9. |  | Point out the environmental issues in construction of i. Hydel power projects ii. Thermal and nuclear power projects iii. Water and air polluting industries and iv. Housing sector . | CO1 | 20 |

ALL THE BEST